## Examiniation System
ACTION PLAN
PROJECT NAME | PROJECT MANAGER
Examiniation System | ITI
ACTION | RESPONSIBLE | PRIORITY | STATUS | START | END | NOTES
Goal #1: Database
RED & Mapping | All memebers | High | Done | 2021-08-03 | 2021-10-03
Database Implmentation | All memebers | High | Done | 2021-11-03 | 2021-12-03
Insert data on database | Abdallah Kotob | High | Done | 2021-12-03 | 2021-12-03
Create proc Student, Course, Topic | Ahmed Hassan | High | Done | 2021-12-03 | 13/3 | 4 proc (Insert, update, delete) and select
Create proc Instructor, Department | Abdelrahman & Abdallah | High | Done | 2021-12-03 | 13/3 | 4 proc (Insert, update, delete) and select
Create proc Questions, Exam, StudentExam | Mostafa Tarek | High | Done | 2021-12-03 | 13/3 | 4 proc (Insert, update, delete) and select
Create proc "Exam Generation" | Ahmed Saad | High | Done | 2021-12-03 | 13/3 | Description at Graduation Project Video
Create proc "Exam Answers" | Ahmed Saad | High | Done | 2021-12-03 | 13/3 | Description at Graduation Project Video
Create proc "Exam Correction" | Ahmed Saad | High | Done | 2021-12-03 | 13/3 | Description at Graduation Project Video
Test all procdures | All memebers | High | Done | 17/3 | 17/3
Maintain Problems | All memebers | High | Done | 17/3 | 19/3
Insert generated data | Mostafa Tarek | Mediem | Done | 17/3 | 18/3 | Insert some real data at first then insert generated data
Goal #2: Desktop Application "Parallel" | Abdelrahman & Abdallah
Student, Course& topic, Instructor "Form" | Abdallah Kotob | High | Done | 13/3 | 19/3
Department, Exam, Question, correction "Form" | Abdelrahman | High | Done | 13/3 | 20/3
Design Application UI | Abdelrahman | Mediem | No | 13/3 | 24/3
Complete the desktop application | Mostafa Tarek | Mediem | No | 21/3 | 24/3
Validation class for input data | Ahmed Hassan | Mediem | No | 24/3 | 25/3
Apply design on the forms colors and fonts |  |  | No
Testing the app | Ahmed Mostafa & Mostafa Tarek | High | No | 25/3 | 26/3
Goal #3: Power BI dashborads & Reports
Report 1 & 2 & 3 | Ahmed Mostafa | High | No | 21/3 | 23/3 | SSRS & deploy them
Report 4 & 5 & 6 | Ahmed Hassan | High | No | 21/3 | 23/3 | SSRS & deploy them
Power BI "design dashboard describe data" | Abdelrahman | High | No | 21/3 | 23/3 | deploy it
Power BI "design dashboard for students & facebook & linkedIn" | Abdallah Kotob | High | No | 21/3 | 23/3 | deploy it
Link Reports and dashboards with desktop application | Mostafa Tarek | High | No | 24/3 | 25/3
Search for real dataset and put it in database | All memebers | High | No | 26/3 | unlimited
Goal #4: Deploy on smarter ASP
Goal #5: Presentation |  |  |  | 26/3
Goal #6: Data Mining |  |  |  | 26/3